## About
Created on: | 22 Nov 20 02:01 UTC
Jira Site: | https://team-1599432850901.atlassian.net
Jira Query: | project = HID AND issuetype = Story AND status = Done ORDER BY created ASC, issuetype ASC, cf[10030] DESC, status ASC

## Your Jira Issues
Issue Type | Key | Summary | Labels | Story Points | Created | Finished
Story | HID-29 | As a user, I want to know that I have reached the correct page to use the SYMCheck application so that I can be sure I am uploading my picture to the correct place and receiving the recommendations/care that I desire | Homepage | 1 | 2020-10-01 02:42 | 2020-10-23 19:39
Story | HID-30 | As a user, I want to be diagnosed by the SYMCheck web application so that I can gain a cursory understanding of what might be causing my symptoms/what the potential recommendations might be | Homepage | 1 | 2020-10-01 03:16 | 2020-11-16 06:58
Story | HID-31 | As a user, I want to upload a photo/image of my symptom/affected area/illness so that the SYMCheck application can diagnose me and I can gain insights as to what I might be afflicted with | UserInputPage | 3 | 2020-10-01 03:16 | 2020-11-04 21:41
Story | HID-32 | As a user, I want to be sure that my image has been uploaded successfully so that I can be sure that the image will be processed by the application so that I can receive recommendations for my care | UserInputPage | 3 | 2020-10-01 03:17 | 2020-11-11 19:01
Story | HID-33 | As a user, I want to submit my image for assessment so that I may receive a[n accurate] determination of my afflciation as well as reccomendations for care | UserInputPage | 8 | 2020-10-01 03:17 | 2020-11-11 18:59
Story | HID-34 | As a user, I want to know if I am in a critical condition or in need of immediate medical attention so that I am able to seek medical care as soon as possible if there is no time to waste! | UserInputPage | 1 | 2020-10-01 03:18 | 2020-11-16 23:12
Story | HID-35 | As a user, I want to find the nearest emergency room so that I can seek immediate medical condition for what I deem to be an extremely critical/dire/time-sensitive condition | UserInputPage | 3 | 2020-10-01 03:18 | 2020-11-16 06:57
Story | HID-36 | As a user, I want to return to the homepage so that I can re-read the SYMCheck mission statement, disclaimer, etc. | UserInputPage | 1 | 2020-10-01 03:19 | 2020-10-26 22:04
Story | HID-37 | As a user, I want to know what my symptoms indicate/what my affliction might be so that I can gain an understanding of what might be causing my symptoms, and thus make an informed decision | ResultsPage | 5 | 2020-10-01 03:19 | 2020-11-16 23:12
Story | HID-38 | As a user, I want to know what information I can obtain about this/any illness I might potentially have so that I can gain an understanding of what might be causing my symptoms, and thus make an informed decision on how best to go forth with my care | ResultsPage | 5 | 2020-10-01 03:20 | 2020-11-16 23:12
Story | HID-39 | As a user, I want to know whether or not I should see a doctor so that I can gauge how much of a PRIORITY a visit to a doctor/medical facility is based on the general nature of my symptoms/illness/affliction | ResultsPage | 5 | 2020-10-01 03:20 | 2020-11-16 23:12
Story | HID-40 | As a user, I want to find the nearest emergency room so that I can receive immediate medical attention if it is deemed necessary | ResultsPage | 3 | 2020-10-01 03:20 | 2020-11-16 06:58
Story | HID-41 | As a user, I want to receive another diagnosis for another affliction/repeat the diagnosis for this one so that so that I can upload another photo/set of symptoms for a different or the same illness (i.e. for confirmation of the latter) | ResultsPage | 1 | 2020-10-01 03:21 | 2020-11-11 19:01
Story | HID-42 | As a user, I want to navigate back to the home page so that to manually start over, or to read SYMCheck's mission statement | ResultsPage | 1 | 2020-10-01 03:21 | 2020-10-26 22:04
Story | HID-43 | As a user, I want to be aware of the quality/accuracy of the results given relative to those from a medical facility/medical professional so that I do not forget that all results are simply cursory recommendations based on past data | ResultsPage | 1 | 2020-10-01 03:21 | 2020-11-16 06:57
Story | HID-44 | As a user, I want to get in touch with the creators of the SYMCheck application so that I can provide the creators of the SYMCheck application with suggestions/comments, ask them questions, commend them for their product, etc. | ResultsPage | 2 | 2020-10-01 03:22 | 2020-10-26 03:51